## Sheet1
| Start Date | End Date | Timeline | Status
Peak Potential | 2024-03-26 | 2024-06-07
Milestone 1 | 2024-03-26 | 2024-04-05 |  | Complete
Define project goals | 2024-03-26 | 2024-04-01 |  | Complete
Research components | 2024-04-02 | 2024-04-04 |  | Complete
Prepare order | 2024-04-04 | 2024-04-05 |  | Complete
Milestone 2 | 2024-04-06 | 2024-04-21 |  | Complete
Create spinning PCB | 2024-04-08 | 2024-04-13 |  | Complete | No real way to test with breadboard
Milestone 3 | 2024-04-22 | 2024-05-05 |  | Complete
Prototype motor control | 2024-04-22 | 2024-04-25 |  | Complete
Test each component with minimal code | 2024-04-22 | 2024-04-25 |  | Complete
Set up backend architecture | 2024-04-22 | 2024-04-26 |  | Active
Test firmware combined with backend | 2024-04-26 | 2024-04-30 |  | Active
Combine all hardware, firmware, and software for full funtionality | 2024-04-30 | 2024-05-05 |  | Active
Milestone 4 | 2024-05-06 | 2024-05-19 |  | Active
Create and order motor control PCB | 2024-05-06 | 2024-05-10 |  | Complete
Prepare order | 2024-05-08 | 2024-05-09 |  | Complete
Refine backend while waiting for parts | 2024-05-08 | 2024-05-14 |  | Complete
Interface new components for new version | 2024-05-15 | 2024-05-19 |  | Complete
Milestone 5 | 2024-05-20 | 2024-06-02 |  | Complete
Research improved code | 2024-05-20 | 2024-05-27 |  | Active
Implement new code and firmware | 2024-05-27 | 2024-06-02 |  | Active
Design 3D printed enclosure | 2024-06-01 | 2024-06-02 |  | Active
Milestone 6 | 2024-05-27 | 2024-06-07 |  | Upcoming
Prepare online project | 2024-05-27 | 2024-06-05 |  | Upcoming
Write report | 2024-06-03 | 2024-06-07 |  | Upcoming
Burndown

## Sheet2
Task Name | Start Date | End Date | Start on Day | Duration
Prodcut Definition | 2025-03-01 | 2025-03-31 | 0 | 30
UI/UX Design | 2025-04-01 | 2025-04-15 | 31 | 14
Feature Development | 2025-04-16 | 2025-04-30 | 46 | 14
Intern Testing and Bug Fixes | 2025-05-01 | 2025-05-15 | 61 | 14
Recruit Beta USers | 2025-05-16 | 2025-05-31 | 76 | 15
Best Testing | 2025-06-01 | 2025-06-30 | 92 | 29
Iteration and Refinements | 2025-07-01 | 2025-07-31 | 122 | 30
Social Media Setup | 2025-07-01 | 2025-07-31 | 122 | 30
Influencer Outreach | 2025-07-16 | 2025-07-31 | 137 | 15
Landing Page and Ads Setup | 2025-08-01 | 2025-08-15 | 153 | 14
Soft Launch (Early Success) | 2025-07-16 | 2025-08-06 | 137 | 21
Post-Launch Growth and KPI's | 2025-10-01 | 2025-12-31 | 214 | 91
AI-Powered Exercise Suggestions | 2025-09-20 | 2025-10-31 | 203 | 41
Workout Builder Development | 2025-11-10 | 2025-12-20 | 254 | 40
AI Workout Coach | 2025-10-20 | 2025-10-31 | 233 | 11
Full Public Launch | 2026-01-01 | 2026-02-28 | 306 | 58